## Sheet1
Contributions
Task Description | Date | Contributor(s)
Ordering Parts | 2023-02-16 | Maria
Design Draft | 2023-02-16 | ALL
Design Revision | 2023-03-07 | ALL
Design Revision | 2023-03-09 | ALL
Setting up ESP32 Bluetooth connection on Arduino IDE | 2023-03-21 | Matthew
Soldering ESP32 and IMU | 2023-03-21 | Maria
Using sockets to receive data to Python over Bluetooth | 2023-03-22 | Jibin
Using data to create scatter plot | 3/28/2023-3/29/2023 | Maria
Research OpenVR | 3/28/2023-3/29/2023 | ALL
Creating simple program for continuous forward movement on OpenVR | 3/28/2023-3/29/2023 | Patrick, Richard
Data conversion program from strings to floats | 3/29/2023, 4/4/2023 | Patrick
Real-time data plot on Python | 2023-04-06 | Maria
Researching socket libraries | 2023-04-07 | Matthew, Patrick, Richard, Jibin
Graph data on SerialPlot | 2023-04-07 | Matthew, Patrick
Simple step counter program | 2023-04-11 | Patrick
Researching filters, step counter algorithms | 4/11/2023 - 4/13/2023 | Matthew, Patrick, Maria
Implement IIR filter | 2023-04-13 | Matthew, Maria, Patrick
Implement step counter (final version) | 2023-04-13 | Matthew, Maria, Patrick
Implement speed calculations | 2023-04-13 | Matthew, Maria, Patrick
Establish Bluetooth connection on OpenVR driver | 2023-04-13 | Jibin, Richard
Fix data corruption and receive proper speed data from the tracker | 2023-04-14 | Richard, Patrick
Test movement on the VR | 4/14/2023, 4/18/2023 | Richard, Matthew
Implement Bluetooth auto-reconnect | 2023-04-18 | Richard, Matthew
Prototype documentation/presentation | 4/18/2023-4/20/2023 | ALL